California Workforce Pathways Joint Advisory Committee

cwpjac-mar20item01

Page 1 of 3

**Attachment 4**

# CALIFORNIA STATE PLAN FOR CAREER TECHNICAL EDUCATION Working Timeline

Posted by the California Department of Education
March 2020

This document is a working timeline for the submission of the federal *Strengthening Career Technical Education for the 21st Century Act* (Perkins V) State Plan, including an extended timeline to complete the comprehensive California State Plan for Career Technical Education (CTE).

## 2019

### Completed:

Jan. 11 The California Workforce Pathways Joint Advisory Committee (CWPJAC) received a presentation on the requirements for the state’s 2019–20 Transition Plan for the Perkins V

Feb. 19 CWPJAC reviewed the Draft Federal 2019–20 California Perkins V State Transition Plan (Transition Plan)

March 11 CWPJAC reviewed and provided input to the Transition Plan

May 8 The State Board of Education (SBE) approved the Transition Plan

May 24 Transition Plan submitted to the United States Department of Education (ED)

July 1 Transition Plan approved by the ED

July 12 CWPJAC received an update on the development of the comprehensive California State Plan for CTE (State Plan for CTE), including requirements for the Perkins V

Aug. 7 Virtual Stakeholder Meeting

Aug. 13 Stakeholder In-Person Meeting #1 – 10:00 a.m. to 3:00 p.m. at the Sacramento County Office of Education’s Conference Center

Sept. 13 CWPJAC reviewed portions of the Draft Federal Perkins V State Plan (Draft Federal State Plan)

Sept. 17 Stakeholder In-Person Meeting #2 – 10:00 a.m. to 5:00 p.m. at the California Community Colleges Chancellor’s Office (CCCCO)

Oct. 11 CWPJAC reviewed portions of the Draft Federal State Plan

Oct. 16 Feedback solicited at the California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA

Oct 17 Kindergarten through grade twelve (K–12) Teacher Feedback Virtual Meeting

Nov. 7 CWPJAC reviewed the first complete Draft Federal State Plan

Nov. 20–22 Feedback solicited at the Association of Career and College Readiness Organizations (CAROCP) CTE Conference, Rancho Mirage, CA

Nov. 25 CWPJAC reviewed a second version of the Draft Federal State Plan

Dec. 2 In-Person Public Input Meeting #1 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference in Anaheim, CA on December 4–7, 2019)

* 10:00 A.M.–12:00 P.M.
* 1:00–3:00 P.M.

 Open the Draft Federal State Plan Public Feedback Survey

Dec. 6 Virtual Public Meeting on the Draft Federal State Plan

Dec. 9 In-Person Public Input Meeting #2 - Christopher Center Building, WestEd Offices, Capitol Room, Sacramento, CA:

* 10:00 A.M.–12:00 P.M.
* 1:00 P.M.–3:00 P.M.

Dec. 11-13 Feedback solicited at the Joint Special Populations Advisory Committee Conference, Sacramento, CA

## 2020

Jan. 3 Close the Draft Federal State Plan Public Feedback Survey

Jan 6 Virtual Accountability Stakeholder Input Session

Jan. 8 SBE Meeting, the Draft Federal State Plan is presented for initial review

Jan. 31 CWPJAC Meeting to review and approve the Draft Federal Perkins V State Plan

### In Progress:

March 2 CWPJAC Meeting – review a final version of the Draft Federal State Plan

March 11 SBE Meeting requesting approval of the Draft Federal State Plan

March 13 The Draft Federal State Plan is sent to the Governor for 30- day review and approval

March 16 Board of Governors Meeting, the Draft Federal State Plan is presented as an informational item

April 12 Anticipated Governor Approval of the Draft Federal State Plan

April 15 Submit California’s Federal Perkins V State Plan (Federal State Plan) to the ED

May 8 CWPJAC Meeting

July 1 Receive the ED’s response to California’s Federal State Plan