# CALIFORNIA STATE PLAN FOR CAREER TECHNICAL EDUCATION Working Timeline

Posted by California Department of Education  
November 2019

This document is a working timeline for the submission of the federal *Strengthening Career Technical Education for the 21st Century Act* (Perkins V) state plan including an extended timeline to complete the full California State Plan for Career Technical Education (CTE).

## 2019

### Completed:

*May 29 California Workforce Pathways Joint Advisory Committee (CWPJAC) Meeting*

*July 12 CWPJAC Meeting*

*Aug. 7 Virtual Stakeholder Meeting*

*Aug. 13 Stakeholder Meeting #1 – 10:00 a.m. to 3:00 p.m. at the Sacramento County Office of Education’s Conference Center*

*Sept. 13 CWPJAC Meeting – Present two-thirds of the State Plan for Career Technical Education (CTE)*

*Sept. 17 Stakeholder Meeting #2 – 10:00 a.m. to 5:00 p.m. at the California Community Colleges Chancellor’s Office (CCCCO)*

*Oct. 2-4 Advance CTE – Perkins Implementation Meeting, Washington DC*

*Oct. 11 CWPJAC Meeting – Present Draft State Plan*

*Oct. 16 California Community College Association for Occupational Education (CCCAOE) Conference, Rancho Mirage, CA – Public Feedback*

*Oct 17 K­–12 Teacher Feedback Virtual Meeting*

### In Progress:

Nov. 08 CWPJAC Meeting – Present the full Draft responses to the California Federal *Strengthening Career and Technical Education for the 21st Century Act* (Perkins V) State Plan and timeline for the California State Plan for CTE

Nov. 11-15 January State Board of Education (SBE) Item due to the Equity and Access Branch (EAB)

Nov. 12 Incorporate CWPJAC comments for the California Federal Perkins V State Plan which will be used at the January SBE Meeting, the January Board of Governors (BOG) Meeting, and the Public Feedback Survey

Nov. 13 SBE Staff to share the California Federal Perkins V State Plan with the Governor

Nov. 13 Public Meeting #1 in Sacramento at the California Department of Public Health Auditorium

Nov. 15 Open the California Federal Perkins V State Plan Public Feedback Survey

Nov. 18 BOG Meeting, Informational Item

Nov. 20-22 Association of Career and College Readiness Organizations (CAROCP) CTE Conference, Rancho Mirage, CA – Public Feedback

Nov. 22 Draft Information Memo Due to the SBE Office for a December Memo

Nov. 25 Draft January Item Due to the SBE Office for the January Meeting Agenda

Dec. 02 Public Meeting #2 - North Orange County Community College District’s Boardroom (prior to the national Association for Career Technical Education Conference [ACTE] in Anaheim on December 4-7, 2019).

* 10:00 A.M.–12:00 P.M.
* 1:00–3:00 P.M.

Dec. Informational Memo to SBE

Dec. 11-13 Joint Special Populations Advisory Committee (JSPAC) Conference – Opportunity for Receiving Public Feedback

Dec. 20 Close the California Federal Perkins V State Plan Public Feedback Survey

Dec. 31 Analyze the California Federal Perkins V State Plan Public Feedback Survey results

## 2020

Jan. 08 SBE Meeting, the Draft California Federal Perkins V State Plan is presented

Jan. 13 BOG Meeting, the Draft California Federal Perkins V State Plan is presented

Jan. 13-17 March SBE Item due to the EAB

Jan. 20 Combine feedback (January SBE Meeting, January BOG Meeting, and the Public Feedback Survey results) into the final California Federal Perkins V State Plan

Jan. 21 CWPJAC Agenda Posting Date for the January 31, 2020 meeting

Jan. 24 Draft Information Memo to the SBE Office for February Memorandum

Jan. 27 Draft SBE Item due to the SBE Office for the March meeting agenda

Jan. 31 CWPJAC Meeting – Review the final California Federal Perkins V State Plan, as well as, Chapters One and Two of the California State Plan for CTE

Feb. 1 Incorporate CWPJAC feedback on the California Federal Perkins V State Plan to present to the SBE in March

March 3 CWPJAC Agenda Posting Date for the March 13, 2020 meeting

March 11-12 SBE Meeting – the final California Federal Perkins V State Plan approved

March 13 CWPJAC Meeting – Review Chapter Three of the California State Plan for CTE

March 13 The final California Federal Perkins V State Plan is sent to the Governor for approval (30 days)

March 16 BOG Meeting, the final California Federal Perkins V State Plan is presented (informational item)

April 12 Governor Approval of the California Federal Perkins V State Plan Complete

April 15 Submit the California Federal Perkins V State Plan to the United States Department of Education

### Extension of Timeline to complete California State Plan for CTE

April 28 CWPJAC Agenda Posting Date for the May 8, 2020 meeting

May 8 CWPJAC Meeting – Present Chapter Four and Five of the California State Plan for CTE

June 30 CWPJAC Agenda posting date for the July 1, 2020 meeting

July 1 Receive the United States Department of Education’s response to California’s submitted California Federal Perkins V State Plan

July 10 CWPJAC Meeting – Present final draft of the California State Plan for CTE

Aug.-Sept. Public Feedback on draft of the California State Plan for CTE

TBD CWPJAC Agenda Posting Date (Sept.)

September CWPJAC Meeting –

TBD CWPJAC Agenda Posting Date (Nov.)

November CWPJAC Meeting – Approval of final draft of the California State Plan for CTE